## Slide 1: Project Planning & Integration Management
1

## Slide 2
2

## Slide 3: What is project integration management?
Project integration management:- involves coordinating all of the other project management knowledge areas throughout a project’s life cycle.
This integration ensures that all the elements of a project come together at the right times to complete a project successfully.
Main processes include
  Develop the project charter
  Develop the project management plan
  Direct and manage project execution
  Monitor and control project work
  Perform integrated change control
  Close the project or phase
Notes: A project charter is the statement of scope, objectives and people who are participating in a project.
It begins the process of defining the roles and responsibilities of those participants and outlines the objectives and goals of the project.

## Slide 4: The Key to Overall Project Success: Good Project Integration Management
4
Project managers must coordinate all of the other knowledge areas throughout a project’s life cycle
Many new project managers have trouble looking at the “big picture” and want to focus on too many details.
Project integration management is not the same thing as software integration.

## Slide 5: Project Integration Management Processes
5
Project Plan Development: taking the results of other planning processes and putting them into a consistent, coherent document—the project plan
Project Plan Execution: carrying out the project plan
Integrated Change Control: coordinating changes across the entire project

## Slide 6: Framework for Project Integration Management
Focus on pulling everything together to reach project success!
6

## Slide 7: Project Plan Development
7
A project plan is a document used to coordinate all project planning documents.
Its main purpose is to guide project execution.
Project plans assist the project manager in leading the project team and assessing project status
Project performance should be measured against a baseline project plan

## Slide 8: Attributes of Project Plans
8
Just as projects are unique, so are project plans:-
  Plans should be dynamic.
  Plans should be flexible.
  Plans should be updated as changes occur.
  Plans should first and foremost guide project execution.

## Slide 9: Common Elements of a Project Plan
9
Introduction or overview of the project.
Description of how the project is organized.
Management and technical processes used on the project.
Work to be done, schedule, and budget information.

## Slide 10: Sample Outline for a Software Project Management Plan (SPMP)
Project Management Plan Sections |  |  |  |  | 
 | Introduction | Project Organization | Managerial Process | Technical Process | Work Packages, Schedule, and Budget
Section | Project | Process model; | Management | Methods, tools, | Work
of | overview; | organizational | objectives and | and | packages;
Topics | project | structure; | priorities; | techniques; | Dependencies;
 | deliverables; | organizational | assumptions, | software | resource
 | evolution of | boundaries and | dependencies, | documentation; | requirements;
 | the SPMP; | interfaces; | and | and project | budget and
 | reference | project | constraints; | support | resource
 | materials; | responsibilities | risk | functions | allocation;
 | definitions and |  | management; |  | and schedule
 | acronyms |  | monitoring |  | 
 |  |  | and |  | 
 |  |  | controlling |  | 
 |  |  | mechanisms; |  | 
 |  |  | and staffing |  | 
 |  |  | plan |  | 
10
IEEE Std 10581-1987

## Slide 11: Stakeholder Analysis
11
A stakeholder analysis documents important (often sensitive) information about stakeholders such as
  stakeholders’ names and organizations
  roles on the project
  unique facts about stakeholders
  level of influence and interest in the project
  suggestions for managing relationships

## Slide 12: Sample Stakeholder Analysis
12
Key Stakeholders |  |  |  |  | 
 | Ahmed | Susan | Erik | Mark | David
Organization | Internal senior management | Project team | Project team | Hardware vendor | Project manager for other internal project
Role on project | Sponsor of project and one of the company's founders | DNA sequencing expert | Lead programmer | Supplies some instrument hardware | Competing for company resources
Unique facts | Demanding, likes details, business focus, Stanford MBA | Very smart, Ph.D. in biology, easy to work with, has a toddler | Best programmer I know, weird sense of humor | Start-up company, he knows we can make him rich if this works | Nice guy, one of oldest people at company, has 3 kids in college
Level of interest | Very high | Very high | High | Very high | Low to medium
Level of influence | Very high; can call the shots | Subject matter expert; critical to success | High; hard to replace | Low; other vendors available | Low to medium
Suggestions on managing relationship | Keep informed, let him lead conversation s ,do as he says and quickly | Make sure she reviews specification s and leads testing; can do some work from home | Keep him happy so he stays; emphasize stock options; likes Mexican food | Give him enough lead time to deliver hardware | He knows his project takes a back seat to this one, but I can learn from him

## Slide 13: Project Plan Execution
13
  Project plan execution involves managing and performing the work described in the project plan.
  The majority of time and money is usually spent on execution.
  The application area or the project directly affects project execution because the products of the project are produced during execution.

## Slide 14: Important Skills for Project Execution
14
General management skills like leadership,
communication, and political skills.
Product skills and knowledge.
Use of specialized tools and techniques.
Notes: What does product knowledge mean? Product knowledge is a skill where your employees fully understand and can effectively communicate with customers about your product, its features, benefits, uses, and support needs.

## Slide 15: Tools and Techniques for Project Execution
15
Work Authorization System: a method for ensuring that qualified people do work at the right time and in the proper sequence.
Status Review Meetings: regularly scheduled meetings used to exchange project information.
Project Management Software: special software to assist in managing projects.

## Slide 17: Integrated Change Control
17
Integrated change control involves identifying, evaluating, and managing changes throughout the project life cycle (Note: 1996 PMBOK called this process “overall change control”)
Three main objectives of change control:
  Determine that a change has occurred
  Influence the factors that create changes to ensure they are beneficial
  Manage actual changes when and as they occur

## Slide 18: Integrated Change Control Process
18

## Slide 19: Change Control on Software Projects
19
Former view: The project team should strive to do exactly what was planned on time and within budget
Problem: Stakeholders rarely agreed up-front on the project scope, and time and cost estimates were inaccurate
Modern view: Project management is a process of constant communication and negotiation
Solution: Changes are often beneficial, and the project team should plan for them

## Slide 20: Change Control System
20
A formal, documented process that describes when and how official project documents and work may be changed
Describes who is authorized to make changes and how to make them
Often includes a Change Control Board (CCB), configuration management, and a process for communicating changes

## Slide 21: Change Control Boards (CCBs)
21
A formal group of people responsible for approving or rejecting changes on a project
Provides guidelines for preparing change requests, evaluates them, and manages the implementation of approved changes
Includes stakeholders from the entire organization

## Slide 22: Making Timely Changes
22
Some CCBs only meet occasionally, so it may take too long for changes to occur
Some organizations have policies in place for time- sensitive changes
  “48 hour policy” allowed project team members to make decisions, then they had 48 hours reverse the decision pending senior management approval
  Delegate changes to the lowest level possible, but keep everyone informed of changes.

## Slide 23: Configuration Management
23
Ensures that the products and their descriptions are correct and complete.
Concentrates on the management of technology by identifying and controlling the functional and physical design characteristics of products
Configuration management specialists identify and document configuration requirements, control changes, record and report changes, and audit the products to verify conformance to requirements

## Slide 24: Suggestions for Managing Integrated Change Control
24
View project management as a process of constant communications and negotiations
Plan for change
Establish a formal change control system, including a Change Control Board (CCB)
Use good configuration management
Define procedures for making timely decisions on smaller changes
Use written and oral performance reports to help identify and manage change
Use project management and other software to help manage and communicate changes

## Slide 25
Project Scope Management

## Slide 26: What is Project Scope Management?
Scope refers to all the work involved in creating the products of the project and the processes used to create them.
Project scope management includes the processes involved in defining and controlling what is or is not included in the project.
The project team and stakeholders must have the same understanding of what products will be produced as a result of a project and what processes will be used in producing them.

## Slide 27: Project Scope Management Processes
Scope planning: developing documents to provide the basis for future project decisions.
Collecting requirements involves defining and documenting the features and functions of the products as well as the processes used for creating them.
Scope definition: involves reviewing the scope management plan, project charter, requirements documents, and organizational process assets to create a scope statement.
Creating the WBS involves subdividing the major project deliverables into smaller, more manageable components.
Validating scope involves formalizing acceptance of the project deliverables.
Scope change control: controlling changes to project scope
Notes: Defining scope involves reviewing the scope management plan, project charter, requirements documents, and organizational process assets to create a scope statement, adding more information as requirements are developed and change requests are approved. Outputs of scope definition are the project scope statement and updates to project documents.
Validating scope involves formalizing acceptance of the project deliverables. Key project stakeholders, such as the customer and sponsor for the project, inspect and then formally accept the deliverables during this process. If thedeliverables are not acceptable, the customer or sponsor usually requests changes.

## Slide 28: Identifying Potential Projects
Many organizations follow a planning process for selecting IT projects
First develop an IT strategic plan based on the organization’s overall strategic plan
Then perform a business area analysis
Then define potential projects
Then select IT projects and assign resources

## Slide 29: Information Technology Planning Process

## Slide 30: Methods for Selecting Projects
There are usually more projects than available time and resources to implement them
It is important to follow a logical process for selecting IT projects to work on
Methods include focusing on broad needs, categorizing projects, financial methods, and weighted scoring models

## Slide 31: Focusing on Broad Organizational Needs
It is often difficult to provide strong justification for many IT projects, but everyone agrees they have a high value.
“It is better to measure gold roughly than to count pennies precisely”
Three important criteria for projects:
  There is a need for the project
  There are funds available
  There’s a strong will to make the project succeed
Notes: One method for selecting projects based on broad organizational needs is to determine whether they first meet three important criteria: need, funding, and will.
Do people in the organization agree that the project needs to be done?
Does the organization have the desire and capacity to provide adequate funds to perform the project?
Is there a strong will to make the project succeed?

## Slide 32: Categorizing IT Projects
One categorization is whether the project addresses
  a problem, an opportunity, or a directive
Another categorization for IT projects is based on timing: How long will it take to complete a project and what is the deadline for completing it?
Another is the overall priority of the project
Notes: Another method for selecting projects is based on various categorizations, such as the project’s impetus, time window, and general priority. The impetus for a project is often to respond to a problem, an opportunity, or a directive. Problems are undesirable situations that prevent an organization from achieving its goals. These problems can be current or anticipated. For example, users of an information system may be having trouble logging on to the system or getting information in a timely manner because the system has reached its capacity. In response, the company could initiate a project to enhance the current system by adding more access lines or upgrading the hardware with a faster processor, more memory, or more storage space. Opportunities are chances to improve the organization. For example, the project described in the chapter’s opening case involves creating a new product that can make or break the entire company. Directives are new requirements imposed by management, government, or some external influence. For example, many projects that involve medical technologies must meet rigorous government requirements .
------------------------------------------
Another categorization for IT projects is based on timing: How long will it take to complete a project and what is the deadline for completing it? For example, some potential projects must be finished within a specific time window; otherwise, they are no longer valid projects. Some projects can be completed very quickly—within a few weeks, days, or even minutes. Many organizations have an end-user support function to handle very small projects that can be completed quickly. However, even though many IT projects can be completed quickly, it is still important to prioritize them.
Organizations can also categorize IT projects as having high, medium, or low priority based on the current business environment. For example, if it is crucial to cut operating costs quickly, projects that have the most potential to do so would be given a high priority. An organization should always complete high-priority projects first, even if a low- or medium-priority project could be finished in less time. Usually an organization has many more potential IT projects than it can undertake at one time, so it is crucial to work on the most important projects first

## Slide 33: Financial Analysis of Projects
Financial considerations are often an important consideration in selecting projects
Three primary methods for determining the projected financial value of projects:
  Net present value (NPV) analysis
  Return on investment (ROI)
  Payback analysis

## Slide 34: Net Present Value Analysis
Net present value (NPV) analysis is a method of calculating the expected net monetary gain or loss from a project by discounting all expected future cash inflows and outflows to the present point in time.
Projects with a positive NPV should be considered if financial value is a key criterion.
The higher the NPV, the better

## Slide 35
Where:
r= discount rate t= year
n= analysis horizon (in years)
* The annual percentage rate that an amount of money is discounted to bring it to a present value
NPV can be computed using the following
Formula.

## Slide 36: Net present value example
Note that totals are equal, but NPVs are
not because of the time value of money.

## Slide 37: Return on Investment
Where
r= rate y=year

## Slide 38: Payback Analysis
Another important financial consideration is payback analysis
Payback period is the amount of time it will take to recoup the total dollars invested in a project, in terms of net cash inflows.
Payback occurs when the net cumulative benefits equal the net cumulative costs or when the net cumulative benefits minus costs equal zero.
Many organizations want IT projects to have a fairly short payback period.

## Slide 39: NPV, ROI, AND PAYBACK ANALYSIS FOR PROJECT 1

## Slide 40: NPV, ROI, and Payback Analysis for Project 2

## Slide 41: Weighted Scoring Model
A weighted scoring model is a tool that provides a systematic process for selecting projects based on many criteria
  First identify criteria important to the project selection process
  Then assign weights (percentages) to each criterion so they add up to 100%
  Then assign scores to each criterion for each project
  Multiply the scores by the weights and get the total weighted scores
The higher the weighted score, the better

## Slide 42
0
10
20
30
40
50
60
70
80
90
Project 4
Project 3
Project 2
Project 1
Since Project 2 has the highest weighted project score, it is the winner!

## Slide 43: Project Charters
After deciding what project to work on, it is important to formalize projects
A project charter is a document that formally recognizes the existence of a project and provides direction on the project’s objectives and management
Key project stakeholders should sign a project charter to acknowledge agreement on the need and intent of the project

## Slide 44: Scope Planning and the Scope Statement
A scope statement is a document used to develop and confirm a common understanding of the project scope. It should include
  a project justification
  a brief description of the project’s products
  a summary of all project deliverables
  a statement of what determines project success

## Slide 45: Scope Planning and the Work Breakdown Structure
After completing scope planning, the next step is to further define the work by breaking it into manageable pieces
Good scope definition
  helps improve the accuracy of time, cost, and resource estimates
  defines a baseline for performance measurement and project control
  aids in communicating clear work responsibilities

## Slide 46: The Work Breakdown Structure
A work breakdown structure (WBS) is an outcome-oriented analysis of the work involved in a project that defines the total scope of the project
It is a foundation document in project management because it provides the basis for planning and managing project schedules, costs, and changes

## Slide 47: Sample Intranet WBS Organized by Product

## Slide 48: Intranet Project … Level-2 WBS
Website design
  Site map
  graphic design
Home page design
  Text
  Images
  Hyperlinks
Marketing pages
Sales pages

## Slide 49: Sample Intranet WBS Organized by Phase

## Slide 50: Approaches to Developing WBSs
Using guidelines: Some organizations, like the DoD, provide guidelines for preparing WBSs
The analogy approach: It often helps to review WBSs of similar projects
The top-down approach: Start with the largest items of the project and keep breaking them down
The bottom-up approach: Start with the detailed tasks and roll them up

## Slide 51: Scope Verification and Scope Change Control
It is very difficult to create a good scope statement and WBS for a project
It is even more difficult to verify project scope and minimize scope changes
Many Software projects suffer from scope creep and poor scope verification
FoxMeyer Drug filed for bankruptcy after scope creep on a robotic warehouse
Engineers at Grumman called a system “Naziware” and refused to use it

## Slide 52: I thank you.