## Slide 1: PROJECT COMMUNICATIONS MANAGEMENT
1

## Slide 2: What is SW project communications management?
2
A subset of project management that includes the processes required to ensure timely and appropriate generation, collection, distribution, storage, and ultimate disposition of project information.

## Slide 3: Importance of Good Communications
3
The greatest threat to many projects is a failure to communicate
Our culture does not portray SW professionals as being good communicators
Research shows that SW professionals must be able to communicate effectively to succeed in their positions
Strong verbal skill is a key factor in career advancement for SW professionals

## Slide 4: Project Communications Management Processes
4
Communications planning: determining the information and communication needs of the stakeholders
Information distribution: making needed information available in a timely manner
Performance reporting: collecting and disseminating performance information
Administrative closure: generating, gathering, and disseminating information to formalize phase or project completion

## Slide 5: Communications Planning
5
Every project should include some type of communications management plan, a document that guides project communications
Creating a stakeholder analysis for project communications also aids in communications planning

## Slide 6: Communications Management Plan Contents
6
A description of a collection and filing structure for gathering and storing various types of information
A distribution structure describing what information goes to
whom, when, and how
A format for communicating key project information
A project schedule for producing the information

## Slide 7
Access methods for obtaining the information
A method for updating the communications management plans as the project progresses and develops
A stakeholder communications analysis
7
…continued

## Slide 8: Sample Stakeholder Analysis for Project Communications
8
Stakeholders | Document Name | Document Format | Contact Person | Due
Customer Management | Monthly Status Report | Hard copy | Gail Feldman, Tony Silva | First of month
Customer Business Staff | Monthly Status Report | Hard copy | Julie Grant, Jeff Martin | First of month
Customer Technical Staff | Monthly Status Report | E-mail | Evan Dodge, Nancy Michaels | First of month
Internal Management | Monthly Status Report | Hard copy | Bob Thomson | First of month
Internal Business and Technical Staff | Monthly Status Report | Intranet | Angie Liu | First of month
Training Subcontractor | Training Plan | Hard Copy | Jonathan Kraus | 11/1/1999
Software Subcontractor | Software Implementation Plan | E-mail | Barbara Gates | 6/1/2000

## Slide 9: Information Distribution
9
Getting the right information to the right people at the right time and in a useful format is just as important as developing the information in the first place
Important considerations include
  using technology to enhance information distribution
  formal and informal methods for distributing information

## Slide 10: THE IMPACT OF THE NUMBER OF PEOPLE ON COMMUNICATIONS CHANNELS
10

## Slide 11: Performance Reporting
Performance reporting keeps stakeholders informed about
how resources are being used to achieve project objectives.
For example
  Status reports describe where the project stands at a specific point in time
  Progress reports describe what the project team has accomplished during a certain period of time
  Project forecasting predicts future project status and progress based on past information and trends
  Status review meetings often include performance reporting
11

## Slide 12: Administrative Closure
It is concerned with generating, gathering, and disseminating information to formalize phase or project completion
A project or phase of a project requires closure
Administrative closure produces
  Project archives
  Formal acceptance
Lessons learned
12

## Slide 13: Conflict Can Be Good
Conflict often produces important results, such as new ideas, better alternatives, and motivation to work harder and more collaboratively
Groupthink can develop if there are no conflicting viewpoints
Research by Karen Jehn suggests that task-related conflict often improves team performance, but emotional conflict often depresses team performance

## Slide 14: Conflict Handling Modes, in Preference Order
Confrontation or problem-solving: directly face a conflict
Compromise: use a give-and-take approach
Smoothing: de-emphasize areas of differences and emphasize areas of agreement
Forcing: the win-lose approach
Withdrawal: retreat or withdraw from an actual or potential
disagreement

## Slide 15: Running Effective Meetings
Define the purpose and intended outcome of the meeting
Determine who should attend the meeting
Provide an agenda to participants before the meeting
Prepare handouts, visual aids, and make logistical arrangements ahead of time
Run the meeting professionally
Build relationships

## Slide 16: DEVELOPING A COMMUNICATIONS INFRASTRUCTURE
A communications infrastructure is a set of tools, techniques, and principles that provide a foundation for the effective transfer of information
  Tools include e-mail, project management software, groupware, fax machines, telephones, teleconferencing systems, document management systems, and word processors
  Techniques include reporting guidelines and templates, meeting ground rules and procedures, decision-making processes, problem-solving approaches, and conflict resolution and negotiation techniques
  Principles include using open dialog and an agreed upon work ethics

## Slide 17: Using E-Mail Effectively
Make sure that e-mail is an appropriate medium for what you want to communicate
Be sure to send the e-mail to the right people
Use meaningful subjects
Limit the content to one main subject, and be as clear and concise as possible
Limit the number and size of attachments
Delete e-mail you don’t need, and don’t open it if you question the source
Make sure your anti-virus software is up to date
Respond to and file e-mails quickly
Learn how to use important features

## Slide 18: Using Templates for Project Communications
Many technical people are afraid to ask for help
Providing examples and templates for project communications saves
time and money
Organizations can develop their own templates, use some provided
by outside organizations, or use samples from textbooks
Recall that research shows that companies that excel in project
management make effective use of templates

## Slide 19: Using Software to Assist in Project Communications
There are many software tools to aid in project communications
Today more than 37 percent of people telecommute or work remotely at least part-time
Project management software includes new capabilities to enhance virtual communications

## Slide 21: What is Risk?
A dictionary definition of risk is “the possibility of loss or injury”
“A risk is a combination of constraint and uncertainty” by Larry Krantz
Project risk management involves understanding potential problems that might occur on the project and how they might impede project success
Risk management is like a form of insurance; it is an investment

## Slide 22: Project Management Maturity by Industry Group and Knowledge Area

## Slide 23: Risk Utility
Risk utility or risk tolerance is the amount of satisfaction or pleasure received from a potential payoff
  Utility rises at a decreasing rate for a person who is risk-averse
  Those who are risk-seeking/taking have a higher tolerance for
risk and their satisfaction increases when more payoff is at stake
  The risk neutral approach achieves a balance between risk and
payoff

## Slide 24: Risk Utility Function and Risk Preference

## Slide 25: WHAT IS PROJECT RISK MANAGEMENT?
Risk management is the systematic process of identifying, analyzing, and responding to project risk.
It includes maximizing the probability and consequences of positive events and minimizing the probability and consequences of adverse events to project objectives.

## Slide 26: Project risk management processes
The goal of project risk management is to minimize potential risks while maximizing potential opportunities. Major processes include
Risk management planning: deciding how to approach and plan the risk management activities for the project
Risk identification: determining which risks are likely to affect a project and documenting their characteristics
Qualitative risk analysis: characterizing and analyzing risks
and prioritizing their effects on project objectives

## Slide 27: …processes
Quantitative risk analysis: measuring the probability and consequences of risks
Risk response planning: taking steps to enhance opportunities and reduce threats to meeting project objectives
Risk monitoring and control: monitoring known risks, identifying new risks, reducing risks, and evaluating the effectiveness of risk reduction

## Slide 28: Risk Management Planning
The main output of risk management planning is a risk management plan
The project team should review project documents and understand the organization’s and the sponsor’s approach to risk
The level of detail will vary with the needs of the project

## Slide 29
Questions Addressed in a Risk Management Plan
Why is it important to take/not take this risk in relation to the project objectives?
What is the specific risk, and what are the risk mitigation deliverables?
How is the risk going to be mitigated? (What risk mitigation approach is to be used?)
Who are the individuals responsible for implementing the risk management plan?
When will the milestones associated with the mitigation approach occur?
How much is required in terms of resources to mitigate risk?

## Slide 30: Contingency and Fallback Plans, Contingency Reserves
Contingency plans are predefined actions that the project
team will take if an identified risk event occurs
Fallback plans are developed for risks that have high impact
on meeting project objectives
Contingency reserve or allowances are provisions held by the project sponsor that can be used to mitigate cost or schedule risk if changes in scope or quality occur

## Slide 31: Risk Identification
Risk identification is the process of understanding what potential unsatisfactory outcomes are associated with a particular project
Several risk identification tools and techniques include
  Interviewing
Brainstorming – group discussion
Delphi technique – panel of experts
SWOT analysis
Read more on these tools and techniques

## Slide 32: Risk identification

## Slide 33: Potential Risk Conditions Associated With Each Knowledge Area
Knowledge Area | Risk Conditions
Integration | Inadequate planning; poor resource allocation; poor integration management; lack of post-project review
Scope | Poor definition of scope or work packages; incomplete definition of quality requirements; inadequate scope control
Time | Errors in estimating time or resource availability; poor allocation and management of float; early release of competitive products
Cost | Estimating errors; inadequate productivity, cost, change, or contingency control; poor maintenance, security, purchasing, etc.
Quality | Poor attitude toward quality; substandard design/materials/workmanship; inadequate quality assurance program
Human Resources | Poor conflict management; poor project organization and definition of responsibilities; absence of leadership
Communications | Carelessness in planning or communicating; lack of consultation with key stakeholders
Risk | Ignoring risk; unclear assignment of risk; poor insurance management
Procurement | Unenforceable conditions or contract clauses; adversarial relations

## Slide 34: Qualitative Risk Analysis
Assess the likelihood and impact of identified risks to
determine their magnitude and priority
Risk quantification tools and techniques include
  Probability/Impact matrixes
  The Top 10 Risk Item Tracking technique
  Expert judgment

## Slide 35: Sample Probability/Impact Matrix for Qualitative Risk Assessment

## Slide 36: Chart Showing High, Medium, and Low-Risk Technologies

## Slide 37: Top 10 Risk Item Tracking
Top 10 Risk Item Tracking is a tool for maintaining an
awareness of risk throughout the life of a project
Establish a periodic review of the top 10 project risk items
List the current ranking, previous ranking, number of times the risk appears on the list over a period of time, and a summary of progress made in resolving the risk item

## Slide 38: Example of Top 10 Risk Item Tracking
 | Monthly Ranking |  |  | 
Risk Item | This Month | Last Month | Number of Months | Risk Resolution Progress
Inadequate planning | 1 | 2 | 4 | Working on revising the entire project plan
Poor definition of scope | 2 | 3 | 3 | Holding meetings with project customer and sponsor to clarify scope
Absence of leadership | 3 | 1 | 2 | Just assigned a new project manager to lead the project after old one quit
Poor cost estimates | 4 | 4 | 3 | Revising cost estimates
Poor time estimates | 5 | 5 | 3 | Revising schedule estimates

## Slide 39: Expert Judgment
Many organizations rely on the intuitive feelings and past experience of experts to help identify potential project risks
Experts can categorize risks as high, medium, or low with or without more sophisticated techniques

## Slide 40: Quantitative Risk Analysis
Often follows qualitative risk analysis, but both can be done together or separately
Large, complex projects involving leading edge technologies often require extensive quantitative risk analysis
Main techniques include
  Decision tree analysis
  Simulation

## Slide 41: Decision Trees and Expected Monetary Value (EMV)
A decision tree is a diagramming method used to help you select the best course of action in situations in which future outcomes are uncertain
EMV is a type of decision tree where you calculate the expected monetary value of a decision based on its risk event probability and monetary value

## Slide 42: Example
Project X has a 60% Probability of success with an impact of Birr 50,000 and has a 40% chance of failure with an impact of Birr- 20,000. What is the Expected Monetary Value of this Project?
EMV of success = Birr 50,000 * 60% = Birr 30,000 EMV of failure = Birr -20,000 * 40% = Birr -8,000 Total EMV = Birr 22,000
In all cases, a positive EMV indicates that it is an opportunity while a negative EMV indicates a Risk/Threat.

## Slide 43: Expected Monetary Value (EMV) Example

## Slide 44: Simulation
Simulation uses a representation or model of a system to
analyze the expected behavior or performance of the system
Monte Carlo analysis simulates a model’s outcome many time to provide a statistical distribution of the calculated results
To use a Monte Carlo simulation, you must have three estimates (most likely, pessimistic, and optimistic) plus an estimate of the likelihood of the estimate being between the optimistic and most likely values

## Slide 45: Sample Monte Carlo Simulation Results for Project Schedule

## Slide 46: Sample Monte Carlo Simulations Results for Project Costs

## Slide 47: Risk Response Planning
After identifying and quantifying risk, you must decide how to respond to them
Four main strategies:
  Risk avoidance: eliminating a specific threat or risk, usually by eliminating its causes
  Risk mitigation: reducing the impact of a risk event by reducing the probability of
its occurrence
  Risk transference: shifting the consequence of a risk and responsibility for its management to a third party
  Risk acceptance: accepting the consequences should a risk occur

## Slide 48: GENERAL RISK MITIGATION STRATEGIES FOR TECHNICAL, COST, AND SCHEDULE RISKS

## Slide 49: Risk Monitoring and Control
Monitoring risks involves knowing their status
Controlling risks involves carrying out the risk management plans as risks occur
Workarounds are unplanned responses to risk events that must be done when there are no contingency plans
The main outputs of risk monitoring and control are corrective action, project change requests, and updates to other plans

## Slide 50: Risk Response Control
Risk response control involves executing the risk management processes and the risk management plan to respond to risk events
Risks must be monitored based on defined milestones and decisions made regarding risks and mitigation strategies
Sometimes workarounds or unplanned responses to risk events are needed when there are no contingency plans

## Slide 51: Thank You!